## EndDate
Data | 411819 | words in book
| 510 | pages in book
| 807 | words per page
Data | 100 | words per minute
| 4118.19 | minutes for the book
| 68.6365 | hours for the book
Process | 2 | hour per day
| 34.3182 | days to record
| 2 | realistic multiplier
| 68.6365 | realistic days to record
| 80.0759 | spare-day each week
| 510 | pages in book
| 7.4304 | pages per day
Information | 2022-02-18 | date tomorrow
| 2022-05-09 01:49 | end date

## Lengths
Sec |  | Words | Days | Minutes | Wds/Min | Thresh | 51 | Cum mins | WAS | NOW
1 | Preface To The First Edition | 1103 | 0.005544 | 7.9833 | 138.1628 |  |  | 7.9833 | 1
2 | Preface To The Third And Fourth Editions | 714 | 0.0030324 | 4.3667 | 163.5115 |  |  | 12.35 | 2
3 | Introduction | 5958 | 0.025313 | 36.45 | 163.4568 |  |  | 48.8 | 3
4 | Book I Of Names And Propositions | 2610 | 0.011273 | 16.2333 | 160.7803 |  |  | 16.2333 | 4
5 | Book I Chapter II Of Names | 12057 | 0.056713 | 81.6667 | 147.6367 | 30.6667 | 5 | 81.6667 | 5 | 6
6 | Book I Chapter III Of The Things Denoted By Names | 16225 | 0.072245 | 104.0333 | 155.9596 | 53.0333 | 6 | 104.0333 | 7 | 8 | 9
7 | Book I Chapter IV Of Propositions | 4783 | 0.022407 | 32.2667 | 148.2335 |  |  | 32.2667 | 10
8 | Book I Chapter V Of The Import Of Propositions | 11591 | 0.05088 | 73.2667 | 158.2029 | 22.2667 | 8 | 73.2667 | 11 | 12
9 | Book I Chapter VI Of Propositions Merely Verbal | 4318 | 0.018843 | 27.1333 | 159.14 |  |  | 27.1333 | 13
10 | Book I Chapter VII Of The Nature Of Classification, And The Five Predicables | 8072 | 0.035266 | 50.7833 | 158.9498 |  |  | 50.7833 | 14
11 | Book I Chapter VIII Of Definition | 12036 | 0.049491 | 71.2667 | 168.8868 | 20.2667 | 11 | 71.2667 | 15 | 16
12 | Book II Of Reasoning | 3875 | 0.017257 | 24.85 | 155.9356 |  |  | 24.85 | 17
13 | Book II Chapter II Of Ratiocination, Or Syllogism | 7928 | 0.042141 | 60.6833 | 130.6454 | 9.6833 | 13 | 60.6833 | 18 | 19
14 | Book II Chapter III Of The Functions And Logical Value Of The Syllogism | 14283 | 0.061956 | 89.2167 | 160.0934 | 38.2167 | 14 | 89.2167 | 20 | 21
15 | Book II Chapter IV Of Trains Of Reasoning, And Deductive Sciences | 6937 | 0.030509 | 43.9333 | 157.8983 |  |  | 43.9333 | 22
16 | Book II Chapter V Of Demonstration, And Necessary Truths | 15088 |  | 97.2376 | 155.1662 | 46.2376 | 16 | 97.2376 | 23 | 24
17 | Book II Chapter VI The Same Subject Continued | 4848 |  | 31.2439 |  |  |  | 31.2439 | 25
18 | Book II Chapter VII Examination Of Some Opinions Opposed To The Preceding Doctrines | 10019 |  | 64.5695 |  | 13.5695 | 18 | 64.5695 | 26 | 27
19 | Book III Of Induction | 2762 |  | 17.8003 |  |  |  | 17.8003 | 28
20 | Book III Chapter II Of Inductions Improperly So Called | 9541 |  | 61.4889 |  | 10.4889 | 20 | 61.4889 | 29 | 30
21 | Book III Chapter III Of The Ground Of Induction | 4451 |  | 28.6854 |  |  |  | 28.6854 | 31
22 | Book III Chapter IV Of Laws Of Nature | 3779 |  | 24.3545 |  |  |  | 24.3545 | 32
23 | Book III Chapter V Of The Law Of Universal Causation | 25776 |  | 166.1186 |  | 115.1186 | 23 | 166.1186 | 33 | 34 | 35
24 | Book III Chapter VI On The Composition Of Causes | 4185 |  | 26.9711 |  |  |  | 26.9711 | 36
25 | Book III Chapter VII On Observation And Experiment | 4342 |  | 27.9829 |  |  |  | 27.9829 | 37
26 | Book III Chapter VIII Of The Four Methods Of Experimental Inquiry | 10087 |  | 65.0077 |  | 14.0077 | 26 | 65.0077 | 38 | 39
27 | Book III Chapter IX Miscellaneous Examples Of The Four Methods | 13808 |  | 88.9884 |  | 37.9884 | 27 | 88.9884 | 40 | 41
28 | Book III Chapter X Of Plurality Of Causes, And Of The Intermixture Of Effects | 10685 |  | 68.8616 |  | 17.8616 | 28 | 68.8616 | 42 | 43
29 | Book III Chapter XI Of The Deductive Method | 4503 |  | 29.0205 |  |  |  | 29.0205 | 44
30 | Book III Chapter XII Of The Explanation Of Laws Of Nature | 4610 |  | 29.7101 |  |  |  | 29.7101 | 45
31 | Book III Chapter XIII Miscellaneous Examples Of The Explanation Of Laws Of Nature | 4942 |  | 31.8497 |  |  |  | 31.8497 | 46
32 | Book III Chapter XIV Of The Limits To The Explanation Of Laws Of Nature; And Of Hypotheses | 11859 |  | 76.4277 |  | 25.4277 | 32 | 76.4277 | 47 | 48
33 | Book III Chapter XV Of Progressive Effects; And Of The Continued Action Of Causes | 3763 |  | 24.2514 |  |  |  | 24.2514 | 49
34 | Book III Chapter XVI Of Empirical Laws | 4497 |  | 28.9818 |  |  |  | 28.9818 | 50
35 | Book III Chapter XVII Of Chance And Its Elimination | 4942 |  | 31.8497 |  |  |  | 31.8497 | 51
36 | Book III Chapter XVIII Of The Calculation Of Chances | 7408 |  | 47.7423 |  |  |  | 47.7423 | 52
37 | Book III Chapter XIX Of The Extension Of Derivative Laws To Adjacent Cases | 3204 |  | 20.6488 |  |  |  | 20.6488 | 53
38 | Book III Chapter XX Of Analogy | 3375 |  | 21.7509 |  |  |  | 42.3997 | 54
39 | Book III Chapter XXI Of The Evidence Of The Law Of Universal Causation | 7972 |  | 51.3772 |  | 0.37716 | 39 | 51.3772 | 55 | 56
40 | Book III Chapter XXII Of Uniformities Of Co-Existence Not Dependent On Causation | 6610 |  | 42.5995 |  |  |  | 42.5995 | 57
41 | Book III Chapter XXIII Of Approximate Generalizations, And Probable Evidence | 6747 |  | 43.4824 |  |  |  | 43.4824 | 58
42 | Book III Chapter XXIV Of The Remaining Laws Of Nature | 9359 |  | 60.316 |  | 9.316 | 42 | 60.316 | 59 | 60
43 | Book III Chapter XXV Of The Grounds Of Disbelief | 8102 |  | 52.215 |  | 1.215 | 43 | 52.215 | 61 | 62
44 | Book IV Of Operations Subsidiary To Induction | 4137 |  | 26.6617 |  |  |  | 26.6617 | 63
45 | Book IV Chapter II Of Abstraction, Or The Formation Of Conceptions | 6819 |  | 43.9464 |  |  |  | 43.9464 | 64
46 | Book IV Chapter III Of Naming, As Subsidiary To Induction | 2256 |  | 14.5392 |  |  |  | 14.5392 | 65
47 | Book IV Chapter IV Of The Requisites Of A Philosophical Language, And The Principles Of Definition | 9081 |  | 58.5243 |  | 7.5243 | 47 | 58.5243 | 66 | 67
48 | Book IV Chapter V On The Natural History Of The Variations In The Meaning Of Terms | 5392 |  | 34.7498 |  |  |  | 34.7498 | 68
49 | Book IV Chapter VI The Principles Of A Philosophical Language Further Considered | 7264 |  | 46.8143 |  |  |  | 46.8143 | 69
50 | Book IV Chapter VII Of Classification, As Subsidiary To Induction | 7206 |  | 46.4405 |  |  |  | 46.4405 | 70
51 | Book IV Chapter VIII Of Classification By Series | 2944 |  | 18.9732 |  |  |  | 18.9732 | 71
52 | Book V On Fallacies | 2323 |  | 14.971 |  |  |  | 33.9442 | 72
53 | Book V Chapter II Classification Of Fallacies | 2967 |  | 19.1214 |  |  |  | 19.1214 | 73
54 | Book V Chapter III Fallacies Of Simple Inspection; Or A Priori Fallacies | 13567 |  | 87.4353 |  | 36.4353 | 54 | 87.4353 | 74 | 75
55 | Book V Chapter IV Fallacies Of Observation | 6167 |  | 39.7445 |  |  |  | 39.7445 | 76
56 | Book V Chapter V Fallacies Of Generalization | 8972 |  | 57.8219 |  | 6.8219 | 56 | 57.8219 | 77 | 78
57 | Book V Chapter VI Fallacies Of Ratiocination | 2856 |  | 18.4061 |  |  |  | 18.4061 | 79
58 | Book V Chapter VII Fallacies Of Confusion | 11277 |  | 72.6769 |  | 21.6769 | 58 | 72.6769 | 80 | 81
59 | Book VI On The Logic Of The Moral Sciences | 1507 |  | 9.7122 |  |  |  | 9.7122 | 82
60 | Book VI Chapter II Of Liberty And Necessity | 3803 |  | 24.5092 |  |  |  | 34.2214 | 83
61 | Book VI Chapter III That There Is, Or May Be, A Science Of Human Nature | 2187 |  | 14.0946 |  |  |  | 48.3159 | 84
62 | Book VI Chapter IV Of The Laws Of Mind | 5151 |  | 33.1967 |  |  |  | 33.1967 | 85
63 | Book VI Chapter V Of Ethology, Or The Science Of The Formation Of Character | 6763 |  | 43.5855 |  |  |  | 43.5855 | 86
64 | Book VI Chapter VI General Considerations On The Social Science | 1696 |  | 10.9302 |  |  |  | 10.9302 | 87
65 | Book VI Chapter VII Of The Chemical, Or Experimental, Method In The Social Science | 3828 |  | 24.6703 |  |  |  | 35.6005 | 88
66 | Book VI Chapter VIII Of The Geometrical, Or Abstract, Method | 3790 |  | 24.4254 |  |  |  | 24.4254 | 89
67 | Book VI Chapter IX Of The Physical, Or Concrete Deductive, Method | 7900 |  | 50.9131 |  |  |  | 50.9131 | 90
68 | Book VI Chapter X Of The Inverse Deductive, Or Historical, Method | 9531 |  | 61.4244 |  | 10.4244 | 68 | 61.4244 | 91 | 92
69 | Book VI Chapter XI Additional Elucidations Of The Science Of History | 6401 |  | 41.2525 |  |  |  | 41.2525 | 93
70 | Book VI Chapter XII Of The Logic Of Practice, Or Art; Including Morality And Policy | 4778 |  | 30.7928 |  |  |  | 30.7928 | 94
|  |  |  | 3056.0002 | minutes
|  |  |  | 50.9333 | hours
[5 empty] | 155.7847 | words per minute average (Chapters)
[7 empty] | 22 | MINIMUM numbert of extra tracks
Count of CDs required

## Sheet4
Sum of hours | Task
Section | Convert | Edit | Read | Grand Total
1 |  | 0.9 | 0.8 | 1.7 | 1.125
2 |  | 1.5 | 0.3 | 1.8 | 5
3 |  | 4.3 | 0.7 | 5 | 6.1429
4 |  | 2.6 | 1.1 | 3.7 | 2.3636
5 |  | 4.1 | 3.3 | 7.4 | 1.2424
6 |  | 6.2 | 1.4 | 7.6 | 4.4286
7 |  | 4.1 | 0.7 | 4.8 | 5.8571
8 |  | 5.2 | 1.9 | 7.1 | 2.7368
9 |  | 2.1 | 0.6 | 2.7 | 3.5
10 |  | 2.1 | 1.2 | 3.3 | 1.75
11 |  | 4.8 | 1.6 | 6.4 | 3
12 |  | 2.9 | 0.4 | 3.3 | 7.25
13 |  | 4.3 | 1.4 | 5.7 | 3.0714
14 | 0.9 | 3.5 | 2.1 | 6.5 | 1.6667
15 | 1 | 3.8 | 0.9 | 5.7 | 4.2222
23 |  | 3.3 | 1 | 4.3 | 3.3
24 |  | 3.2 | 1 | 4.2 | 3.2
25 |  | 0.6 | 0.8 | 1.4 | 0.75
26 |  | 1.8 | 1 | 2.8 | 1.8
27 |  | 0.8 | 1 | 1.8 | 0.8
28 |  | 0.6 | 0.5 | 1.1 | 1.2
29 |  | 1.3 | 0.5 | 1.8 | 2.6
30 |  | 0.6 | 1 | 1.6 | 0.6
31 |  | 0.8 | 0.8 | 1.6 | 1
32 |  | 0.5 | 0.6 | 1.1 | 0.83333
33 |  | 2 | 1.2 | 3.2 | 1.6667
34 |  | 2.1 | 1.5 | 3.6 | 1.4
35 |  | 1.1 | 0.9 | 2 | 1.2222
36 |  | 1 | 0.5 | 1.5 | 2
37 |  | 0.9 | 0.5 | 1.4 | 1.8
38 |  | 1.6 | 0.7 | 2.3 | 2.2857
39 |  | 1 | 0.6 | 1.6 | 1.6667
40 |  | 2 | 1 | 3 | 2
41 |  | 1.7 | 1.3 | 3 | 1.3077
42 |  | 1.5 | 0.9 | 2.4 | 1.6667
43 |  | 0.9 | 0.5 | 1.4 | 1.8
Grand Total | 1.9 | 91.3 | 36.2 | 129.4 | 2.4515
233727
1806.2365
232200

## Billing
date | time | AmPm | hours | Project | Task | Section
2022-02-18 | 7:42 | AM | 0.4 | Mill | Edit | 1
2022-02-17 | 2:32 | PM | 0.5 | Mill | Edit | 1
2022-02-16 | 9:07 | AM | 0.8 | Mill | Read | 1
2022-02-17 | 3:05 | PM | 1.5 | Mill | Edit | 2
2022-02-17 | 12:02 | PM | 0.3 | Mill | Read | 2
2022-03-04 | 7:07 | AM | 1.6 | Mill | edit | 3
2022-03-05 | 8:33 | AM | 1 | Mill | Edit | 3
2022-03-05 | 10:01 | AM | 1 | Mill | Edit | 3
2022-03-05 | 11:25 | AM | 0.7 | Mill | Edit | 3
2022-02-17 | 1:26 | PM | 0.7 | Mill | Read | 3
2022-02-22 | 7:37 | AM | 2.1 | Mill | Edit | 4
2022-02-18 | 9:05 | AM | 0.5 | Mill | Edit | 4
2022-02-18 | 8:40 | AM | 0.4 | Mill | Read | 4
2022-02-21 | 4:55 | PM | 0.7 | MILL | Read | 4
2022-02-22 | 11:32 | AM | 1.9 | Mill | Edit | 5
2022-03-05 | 1:55 | PM | 1.3 | Mill | Edit | 5
2022-03-09 | 9:05 | AM | 0.6 | mill | edit | 5
2022-03-11 | 10:29 | AM | 0.3 | mill | edit | 5
2022-02-18 | 3:59 | PM | 1 | Mill | Read | 5
2022-02-21 | 5:35 | PM | 1.1 | MILL | Read | 5
2022-02-22 | 10:23 | AM | 1.2 | Mill | Read | 5
2022-02-22 | 5:13 | PM | 1.5 | Mill | Edit | 6
2022-02-23 | 10:35 | AM | 2.8 | Mill | Edit | 6
2022-03-05 | 4:12 | PM | 1.9 | mill | edit | 6
2022-02-22 | 2:21 | PM | 0.4 | Mill | Read | 6
2022-02-23 | 9:20 | AM | 1 | Mill | Read | 6
2022-02-23 | 4:44 | PM | 1.1 | Mill | Edit | 7
2022-03-06 | 11:12 | AM | 1.6 | mill | edit | 7
2022-03-10 | 8:05 | AM | 0.4 | mill | edit | 7
2022-03-11 | 3:30 | PM | 0.6 | mill | edit | 7
2022-03-12 | 8:23 | AM | 0.4 | mill | edit | 7
2022-02-23 | 4:05 | PM | 0.7 | Mill | Read | 7
2022-02-24 | 4:32 | PM | 2.1 | Mill | Edit | 8
2022-02-24 | 7:13 | PM | 1.1 | Mill | Edit | 8
2022-02-24 | 8:19 | PM | 0 | Mill | Edit | 8
2022-03-06 | 1:58 | PM | 1.5 | mill | edit | 8
2022-03-07 | 10:04 | AM | 0.5 | mill | edit | 8
2022-02-24 | 2:14 | PM | 1.3 | Mill | Read | 8
2022-02-24 | 3:58 | PM | 0.6 | Mill | Read | 8
2022-02-25 | 10:32 | AM | 0.9 | Mill | Edit | 9
2022-02-25 | 11:26 | AM | 0 | Mill | Edit | 9
2022-03-06 | 3:31 | PM | 1.2 | mill | edit | 9
2022-02-25 | 9:31 | AM | 0.6 | Mill | Read | 9
2022-02-25 | 1:52 | PM | 1.1 | Mill | Edit | 10
2022-02-25 | 3:00 | PM | 0.1 | Mill | Edit | 10
2022-03-06 | 5:50 | PM | 0.9 | mill | edit | 10
2022-02-25 | 12:02 | PM | 0.7 | Mill | Read | 10
2022-02-25 | 1:22 | PM | 0.5 | Mill | Read | 10
2022-02-26 | 10:19 | AM | 0.5 | mill | edit | 11
2022-02-26 | 10:50 | AM | 1.5 | mill | edit | 11
2022-03-07 | 11:08 | AM | 1.1 | mill | edit | 11
2022-03-15 | 2:34 | PM | 0.7 | mill | edit | 11
2022-03-15 | 5:39 | PM | 1 | mill | edit | 11
2022-02-26 | 8:29 | AM | 1.6 | Mill | Read | 11
2022-02-26 | 5:36 | PM | 0.7 | mill | edit | 12
2022-03-07 | 12:25 | PM | 1.8 | mill | edit | 12
2022-03-09 | 9:43 | AM | 0.4 | mill | edit | 12
2022-02-26 | 5:09 | PM | 0.4 | mill | read | 12
2022-02-24 | 10:38 | AM | 1.7 | Mill | Edit | 13
2022-02-24 | 12:23 | PM | 0.1 | Mill | Edit | 13
2022-03-07 | 2:13 | PM | 1.1 | mill | edit | 13
2022-03-15 | 3:14 | PM | 0.8 | mill | edit | 13
2022-03-16 | 2:42 | PM | 0.6 | mill | edit | 13
2022-02-24 | 4:53 | AM | 1.4 | Mill | Read | 13
2022-03-02 | 5:32 | PM | 0.9 | Mill | Convert | 14
2022-02-27 | 1:25 | PM | 1.5 | mill | edit | 14
2022-03-07 | 3:39 | PM | 1.5 | mill | edit | 14
2022-03-16 | 3:19 | PM | 0.5 | mill | edit | 14
2022-02-27 | 9:22 | AM | 1.2 | mill | read | 14
2022-02-27 | 11:17 | AM | 0.9 | mill | read | 14
2022-03-02 | 4:32 | PM | 1 | Mill | Convert | 15
2022-02-28 | 10:48 | AM | 1.5 | mill | edit | 15
2022-03-07 | 6:24 | PM | 1 | mill | edit | 15
2022-03-09 | 10:08 | AM | 0.5 | mill | edit | 15
2022-03-16 | 9:35 | AM | 0.8 | mill | edit | 15
2022-02-28 | 9:38 | AM | 0.9 | mill | read | 15
2022-03-07 | 7:24 | PM | 0.9 | mill | edit | 16
2022-03-16 | 4:21 | PM | 0.3 | mill | edit | 16
2022-03-08 | 7:31 | AM | 1.1 | mill | edit | 17
2022-03-16 | 4:38 | PM | 1.1 | mill | edit | 17
2022-03-08 | 10:18 | AM | 1.2 | mill | edit | 18
2022-03-10 | 4:32 | PM | 1 | MILL | EDIT | 18
2022-03-08 | 11:51 | AM | 0.8 | mill | edit | 19
2022-03-12 | 2:35 | PM | 0.3 | mill | edit | 19
2022-03-14 | 11:35 | AM | 1.4 | mill | edit | 21
2022-03-16 | 11:49 | AM | 0.5 | MILL | EDIT | 22
2022-03-16 | 1:22 | PM | 1 | MILL | EDIT | 22
2022-03-03 | 10:59 | AM | 1 | mill | edit | 23
2022-03-08 | 3:54 | PM | 1.6 | mill | edit | 23
2022-03-14 | 12:56 | PM | 0.7 | mill | edit | 23
2022-03-03 | 9:50 | AM | 1 | mill | read | 23
2022-03-04 | 2:37 | PM | 1 | Mill | EDit | 24
2022-03-09 | 10:50 | AM | 1.9 | mill | edit | 24
2022-03-17 | 3:54 | PM | 0.3 | mill | edit | 24
2022-03-04 | 1:13 | PM | 1 | Mill | Read | 24
2022-03-09 | 2:44 | PM | 0.6 | Mill | edit | 25
2022-03-09 | 1:56 | PM | 0.8 | Mill | read | 25
2022-03-09 | 4:48 | PM | 1.2 | mill | edit | 26
2022-03-18 | 8:37 | AM | 0.6 | mill | edit | 26
2022-03-09 | 3:47 | PM | 1 | mill | read | 26
2022-03-10 | 3:21 | PM | 0.8 | mill | edit | 27
2022-03-10 | 2:21 | PM | 1 | mill | read | 27
2022-03-11 | 2:53 | PM | 0.6 | mill | edit | 28
2022-03-11 | 2:24 | PM | 0.5 | mill | read | 28
2022-03-11 | 4:58 | PM | 1.3 | mill | edit | 29
2022-03-11 | 4:28 | PM | 0.5 | mill | read | 29
2022-03-11 | 7:55 | PM | 0.6 | mill | edit | 30
2022-03-11 | 6:15 | PM | 1 | mill | read | 30
2022-03-12 | 1:47 | PM | 0.8 | mill | edit | 31
2022-03-12 | 12:38 | PM | 0.8 | mill | read | 31
2022-03-12 | 4:08 | PM | 0.5 | mill | edit | 32
2022-03-12 | 3:30 | PM | 0.6 | mill | read | 32
2022-03-13 | 2:06 | PM | 2 | mill | edit | 33
2022-03-13 | 12:54 | PM | 1.2 | mill | read | 33
2022-03-14 | 4:13 | PM | 2.1 | mill | edit | 34
2022-03-14 | 2:43 | PM | 1.5 | mill | read | 34
2022-03-15 | 9:51 | AM | 0.6 | mill | edit | 35
2022-03-15 | 10:59 | AM | 0.5 | mill | edit | 35
2022-03-15 | 9:23 | AM | 0.5 | mill | read | 35
2022-03-15 | 10:36 | AM | 0.4 | mill | read | 35
2022-03-15 | 4:34 | PM | 1 | mill | edit | 36
2022-03-15 | 4:03 | PM | 0.5 | mill | read | 36
2022-03-16 | 8:38 | AM | 0.9 | mill | edit | 37
2022-03-16 | 7:52 | AM | 0.5 | mill | read | 37
2022-03-17 | 1:10 | PM | 1.6 | mill | edit | 38
2022-03-16 | 5:42 | PM | 0.7 | mill | read | 38
2022-03-17 | 4:29 | PM | 1 | mill | edit | 39
2022-03-17 | 3:07 | PM | 0.6 | mill | read | 39
2022-03-18 | 10:45 | AM | 0.8 | mill | edit | 40
2022-03-18 | 12:16 | PM | 1.2 | mill | edit | 40
2022-03-18 | 9:38 | AM | 1 | mill | read | 40
2022-03-18 | 5:45 | PM | 1.7 | mill | edit | 41
2022-03-18 | 2:58 | PM | 0.7 | mill | read | 41
2022-03-18 | 5:11 | PM | 0.6 | mill | read | 41
2022-03-19 | 11:33 | AM | 1.5 | mill | edit | 42
2022-03-19 | 10:18 | AM | 0.9 | mill | read | 42
2022-03-19 | 3:39 | PM | 0.9 | mill | edit | 43
2022-03-19 | 2:49 | PM | 0.5 | mill | read | 43

## NewSections
x`x` | Sec | Greek | Section title |  | Page | Pages | Words | Length | Lcumul | WordsCum | %Cumul | Target | LengthCum | Uploaded | PLOK | Notes
2022-02-16 | 1 |  | Preface To The First Edition |  | 3 | 3 | 1266 | 0:08 | 0:08 | 1266 | 0.2665% |  |  | 2022-02-18 | Y | 0
2022-02-16 | 2 |  | Preface To The Third And Fourth Editions |  | 7 | 4 | 705 | 0:04 | 0:12 | 1971 | 0.415% |  |  | 2022-02-17 | Y | 0
2022-02-17 | 3 |  | Introduction |  | 17 | 10 | 5957 | 0:36 | 0:49 | 7928 | 1.669% |  |  | 2022-03-05 | Y | 0
2022-02-17 | 4 |  | Book I Chapter I Of Names And Propositions |  | 26 | 9 | 2609 | 0:16 | 1:05 | 10537 | 2.218% |  |  | 2022-03-05 | Y | 0
2022-02-18 | 5 | y | Book I Chapter II Of Names; Parts 1 through 4 | 1 of 2 | 29 | 3 | 5229 | 0:25 | 1:30 | 15766 | 3.319% |  |  | 2022-03-09 | Y | 0
2022-02-19 | 6 |  | Book I Chapter II Of Names; Parts 5 through 8 | 2 of 2 | 37 | 8 | 6854 | 0:51 | 2:21 | 22620 | 4.762% |  |  | 2022-03-05 | Y | 0
2022-02-20 | 7 | y | Book I Chapter III Of The Things Denoted By Names; Parts 1 through 5 | 1 of 3 | 45 | 8 | 5228 | 0:32 | 2:54 | 27848 | 5.863% |  |  | 2022-03-06 | Y | 0
2022-02-21 | 8 |  | Book I Chapter III Of The Things Denoted By Names; Parts 6 through 9 | 2 of 3 | 52 | 7 | 5828 | 0:38 | 3:31 | 33676 | 7.09% |  |  | 2022-03-07 | Y | 0
2022-02-21 | 9 |  | Book I Chapter III Of The Things Denoted By Names; Parts 10 through 15 | 3 of 3 | 59 | 7 | 5232 | 0:34 | 4:06 | 38908 | 8.191% |  |  | 2022-03-06 | Y | 0
2022-02-22 | 10 |  | Book I Chapter IV Of Propositions |  | 66 | 7 | 4778 | 0:32 | 4:38 | 43686 | 9.197% |  |  | 2022-03-06 | Y | 0
2022-02-23 | 11 | Y | Book I Chapter V Of The Import Of Propositions Parts 1 through 3 | 1 of 2 | 73 | 7 | 5450 | 0:34 | 5:12 | 49136 | 10.34% |  |  | 2022-03-07 | Y | 0
2022-02-24 | 12 |  | Book I Chapter V Of The Import Of Propositions Parts 4 through 7 | 2 of 2 | 80 | 7 | 6164 | 0:39 | 5:52 | 55300 | 11.64% |  |  | 2022-03-09 | Y | 0
2022-02-25 | 13 | y | Book I Chapter VI Of Propositions Merely Verbal |  | 88 | 8 | 4311 | 0:27 | 6:19 | 59611 | 12.55% |  |  | 2022-03-07 | Y | 0
2022-02-26 | 14 | y | Book I Chapter VII Of The Nature Of Classification, And The Five Predicables |  | 94 | 6 | 8059 | 0:50 | 7:09 | 67670 | 14.25% |  |  | 2022-03-07 | Y | 0
2022-02-27 | 15 |  | Book I Chapter VIII Of Definition Parts 1 through 4 | 1 of 2 | 105 | 11 | 6470 | 0:30 | 7:39 | 74140 | 15.61% |  |  | 2022-03-07 | Y | 0
2022-02-28 | 16 | y | Book I Chapter VIII Of Definition Parts 5 through 7 | 2 of 2 | 113 | 8 | 5596 | 0:41 | 8:20 | 79736 | 16.79% |  |  | 2022-03-07 | Y | 0
2022-02-28 | 17 | y | Book II Chapter I Of Reasoning |  | 121 | 8 | 3886 | 0:25 | 8:45 | 83622 | 17.61% |  |  | 2022-03-08 | Y | 0
2022-03-01 | 18 |  | Book II Chapter II Of Ratiocination, Or Syllogism Part 1 | 1 of 2 | 126 | 5 | 4509 | 0:34 | 9:19 | 88131 | 18.55% |  |  | 2022-03-08 | Y | 0
2022-03-02 | 19 |  | Book II Chapter II Of Ratiocination, Or Syllogism Part 2 through 4 | 2 of 2 | 132 | 6 | 4949 | 0:31 | 9:50 | 93080 | 19.6% |  |  | 2022-03-08 | Y | 0
2022-03-03 | 20 |  | Book II Chapter III Of The Functions And Logical Value Of The Syllogism Parts 1 through 4 | 1 of 2 | 139 | 7 | 6836 | 0:43 | 10:33 | 99916 | 21.04% |  |  | 2022-03-02 | Y | 0
2022-03-04 | 21 |  | Book II Chapter III Of The Functions And Logical Value Of The Syllogism Parts 5 through 9 | 2 of 2 | 148 | 9 | 7466 | 0:47 | 11:19 | 107382 | 22.61% |  |  | 2022-03-02 | Y | 0
2022-03-05 | 22 |  | Book II Chapter IV Of Trains Of Reasoning, And Deductive Sciences |  | 158 | 10 | 6926 | 0:44 | 12:03 | 114308 | 24.07% |  |  | 2022-03-02 | Y | 0
2022-03-06 | 23 |  | Book II Chapter V Of Demonstration, And Necessary Truths Parts 1 through 5 | 1 of 2 | 168 | 10 | 7013 | 0:43 | 12:46 | 121321 | 25.54% |  |  | 2022-03-08 | Y | 0
2022-03-07 | 24 |  | Book II Chapter V Of Demonstration, And Necessary Truths Part 6 | 2 of 2 | 177 | 9 | 8099 | 0:50 | 13:37 | 129420 | 27.25% |  |  | 2022-03-09 | Y | 0
2022-03-08 | 25 |  | Book II Chapter VI The Same Subject Continued |  | 187 | 10 | 4841 | 0:33 | 14:09 | 134261 | 28.27% |  |  | 2022-03-09 | Y | 0
2022-03-09 | 26 |  | Book II Chapter VII Examination Of Some Opinions Opposed To The Preceding Doctrines Parts 1 through 3 | 1 of 2 | 193 | 6 | 5835 | 0:41 | 14:50 | 140096 | 29.49% |  |  | 2022-03-09 | Y | 0
2022-03-09 | 27 |  | Book II Chapter VII Examination Of Some Opinions Opposed To The Preceding Doctrines Parts 4 through 5 | 2 of 2 | 200 | 7 | 4204 | 0:25 | 15:15 | 144300 | 30.38% |  |  | 2022-03-10 | Y | 0
2022-03-10 | 28 |  | Book III. Of Induction. Chapter I. Preliminary Observations On Induction In General. |  | 207 | 7 | 2666 | 0:17 | 15:32 | 146966 | 30.94% |  |  | 2022-03-11 | Y | 0
2022-03-10 | 29 |  | Book III Chapter II Of Inductions Improperly So Called Parts 1 through 3 | 1 of 2 | 210 | 3 | 4201 | 0:20 | 15:52 | 151167 | 31.83% |  |  | 2022-03-11 | Y | 0
2022-03-11 | 30 |  | Book III Chapter II Of Inductions Improperly So Called Parts 4 through 5 | 2 of 2 | 216 | 6 | 5365 | 0:42 | 16:34 | 156532 | 32.96% |  |  | 2022-03-11 | Y | 0
2022-03-12 | 31 |  | Book III Chapter III Of The Ground Of Induction |  | 223 | 7 | 4444 | 0:28 | 17:02 | 160976 | 33.89% |  |  | 2022-03-12 | Y | 0
2022-03-12 | 32 |  | Book III Chapter IV Of Laws Of Nature |  | 229 | 6 | 3772 | 0:25 | 17:27 | 164748 | 34.68% |  |  | 2022-03-12 | Y | 0
2022-03-14 | 33 |  | Book III Chapter V Of The Law Of Universal Causation Parts 1 through 5 | 1 of 3 | 234 | 5 | 8319 | 0:53 | 18:20 | 173067 | 36.44% |  |  | 2022-03-13 | Y | 0
2022-03-15 | 34 |  | Book III Chapter V Of The Law Of Universal Causation Parts 6 through 10 | 2 of 3 | 245 | 11 | 8367 | 0:56 | 19:16 | 181434 | 38.2% |  |  | 2022-03-14 | Ready | 0
2022-03-16 | 35 | Y | Book III Chapter V Of The Law Of Universal Causation Part 11 | 3 of 3 | 256 | 11 | 9148 | 1:01 | 20:17 | 190582 | 40.12% |  |  | 2022-03-26 | Ready | 0
2022-03-17 | 36 |  | Book III Chapter VI On The Composition Of Causes |  | 266 | 10 | 4177 | 0:27 | 20:44 | 194759 | 41% |  |  | 2022-03-15 | Ready | 0
2022-03-18 | 37 |  | Book III Chapter VII On Observation And Experiment |  | 272 | 6 | 4335 | 0:28 | 21:12 | 199094 | 41.92% |  |  | 2022-03-16 | Ready | 0
2022-03-18 | 38 |  | Book III Chapter VIII Of The Four Methods Of Experimental Inquiry Parts 1 through 4 | 1 of 2 | 278 | 6 | 4753 | 0:34 | 21:45 | 203847 | 42.92% |  |  | 2022-03-19 | Ready | 0
2022-03-19 | 39 |  | Book III Chapter VIII Of The Four Methods Of Experimental Inquiry Parts 5 through 7 | 2 of 2 | 285 | 7 | 5353 | 0:35 | 22:21 | 209200 | 44.04% |  |  | 2022-03-19 | Ready | 0
2022-03-20 | 40 |  | Book III Chapter IX Miscellaneous Examples Of The Four Methods Parts 1 through 3 | 1 of 2 | 292 | 7 | 6935 | 0:45 | 23:06 | 216135 | 45.5% |  |  | 2022-03-19 | Ready | 0
2022-03-21 | 41 |  | Book III Chapter IX Miscellaneous Examples Of The Four Methods Parts 4 through 6 | 2 of 2 | 301 | 9 | 6892 | 0:44 | 23:51 | 223027 | 46.95% |  |  | 2022-03-19 | Ready | 0
2022-03-22 | 42 |  | Book III Chapter X Of Plurality Of Causes, And Of The Intermixture Of Effects Parts 1 through 5 | 1 of 2 | 311 | 10 | 5577 | 0:45 | 24:36 | 228604 | 48.13% |  |  | 2022-03-19 | Ready | 0
2022-03-23 | 43 |  | Book III Chapter X Of Plurality Of Causes, And Of The Intermixture Of Effects Parts 6 through 8 | 2 of 2 | 318 | 7 | 5123 | 0:26 | 25:02 | 233727 | 49.21% |  |  | 2022-03-19 | Ready | 0
2022-03-24 | 44 |  | Book III Chapter XI Of The Deductive Method |  | 325 | 7 | 4496 | 0:29 | 25:30 | 238223 | 50.15% |  |  | 2022-03-20 | Ready | 0
2022-03-24 | 45 |  | Book III Chapter XII Of The Explanation Of Laws Of Nature |  | 332 | 7 | 4600 | 0:29 | 26:00 | 242823 | 51.12% |  |  | 2022-03-20 | Ready | 0
2022-03-25 | 46 |  | Book III Chapter XIII Miscellaneous Examples Of The Explanation Of Laws Of Nature |  | 338 | 6 | 4930 | 0:33 | 26:33 | 247753 | 52.16% |  |  | 2022-03-21 | Ready | 0
2022-03-26 | 47 |  | Book III Chapter XIV Of The Limits To The Explanation Of Laws Of Nature; And Of Hypotheses Parts 1 through 4 | 1 of 2 | 345 | 7 | 6156 | 0:40 | 27:13 | 253909 | 53.46% |  |  | 2022-03-21 | Ready | 0
2022-03-27 | 48 |  | Book III Chapter XIV Of The Limits To The Explanation Of Laws Of Nature; And Of Hypotheses Parts 5 through 7 | 2 of 2 | 353 | 8 | 5718 | 0:36 | 27:50 | 259627 | 54.66% |  |  | 2022-03-22 | Ready | 0
2022-03-27 | 49 |  | Book III Chapter XV Of Progressive Effects; And Of The Continued Action Of Causes |  | 361 | 8 | 3749 | 0:24 | 28:14 | 263376 | 55.45% |  |  | 2022-03-22 | Ready | 0
2022-03-28 | 50 |  | Book III Chapter XVI Of Empirical Laws |  | 366 | 5 | 4491 | 0:29 | 28:43 | 267867 | 56.39% |  |  | 2022-03-22 | Ready | 0
2022-03-29 | 51 |  | Book III Chapter XVII Of Chance And Its Elimination |  | 372 | 6 | 4934 | 0:31 | 29:14 | 272801 | 57.43% |  |  | 2022-03-22 | Ready | 0
2022-03-30 | 52 |  | Book III Chapter XVIII Of The Calculation Of Chances |  | 379 | 7 | 7400 | 0:47 | 30:01 | 280201 | 58.99% |  |  | 2022-03-23 | Ready | 0
2022-03-30 | 53 |  | Book III Chapter XIX Of The Extension Of Derivative Laws To Adjacent Cases |  | 389 | 10 | 3192 | 0:21 | 30:22 | 283393 | 59.66% |  |  | 2022-03-23 | Ready | 0
2022-03-31 | 54 |  | Book III Chapter XX Of Analogy |  | 393 | 4 | 3370 | 0:22 | 30:44 | 286763 | 60.37% |  |  | 2022-03-23 | Ready | 0
2022-03-31 | 55 | Y | Book III Chapter XXI Of The Evidence Of The Law Of Universal Causation Part 1 | 1 of 2 | 397 | 4 | 2486 | 0:16 | 31:00 | 289249 | 60.9% |  |  | 2022-03-24 | Ready | 0
2022-04-01 | 56 |  | Book III Chapter XXI Of The Evidence Of The Law Of Universal Causation Parts 2 through 4 | 2 of 2 | 401 | 4 | 5512 | 0:35 | 31:35 | 294761 | 62.06% |  |  | 2022-03-24 | Ready | 0
2022-04-02 | 57 |  | Book III Chapter XXII Of Uniformities Of Co-Existence Not Dependent On Causation |  | 406 | 5 | 6597 | 0:43 | 32:18 | 301358 | 63.45% |  |  | 2022-03-27 | Ready | 0
2022-04-03 | 58 |  | Book III Chapter XXIII Of Approximate Generalizations, And Probable Evidence |  | 416 | 10 | 6740 | 0:44 | 33:02 | 308098 | 64.86% |  |  | 2022-03-28 | Ready | 0
2022-04-04 | 59 |  | Book III Chapter XXIV Of The Remaining Laws Of Nature Parts 1 through 5 | 1 of 2 | 425 | 9 | 5088 | 0:35 | 33:37 | 313186 | 65.94% |  |  | 2022-03-28 | Ready | 0
2022-04-04 | 60 | Y | Book III Chapter XXIV Of The Remaining Laws Of Nature Parts 6 through 9 | 2 of 2 | 431 | 6 | 4292 | 0:28 | 34:05 | 317478 | 66.84% |  |  | 2022-03-29 | Ready | 0
2022-04-05 | 61 |  | Book III Chapter XXV Of The Grounds Of Disbelief Parts 1 through 3 | 1 of 2 | 438 | 7 | 4100 | 0:27 | 34:32 | 321578 | 67.7% |  |  | 2022-03-29 | Ready | 0
2022-04-06 | 62 |  | Book III Chapter XXV Of The Grounds Of Disbelief Parts 4 through 6 | 2 of 2 | 443 | 5 | 4023 | 0:26 | 34:58 | 325601 | 68.55% |  |  | 2022-03-30 | Ready | 0
2022-04-06 | 63 |  | Book IV Chapter I Of Operations Subsidiary To Induction |  | 449 | 6 | 4132 | 0:24 | 35:22 | 329733 | 69.42% |  |  | 2022-03-30 | Ready | 0
2022-04-07 | 64 |  | Book IV Chapter II Of Abstraction, Or The Formation Of Conceptions |  | 455 | 6 | 6808 | 0:43 | 36:05 | 336541 | 70.85% |  |  | 2022-03-30 | Ready | 0
2022-04-08 | 65 |  | Book IV Chapter III Of Naming, As Subsidiary To Induction |  | 464 | 9 | 2246 | 0:15 | 36:19 | 338787 | 71.33% |  |  | 2022-03-31 | Ready | 0
2022-04-08 | 66 |  | Book IV Chapter IV Of The Requisites Of A Philosophical Language, And The Principles Of Definition Parts 1 through 4 | 1 of 2 | 467 | 3 | 3781 | 0:24 | 36:43 | 342568 | 72.12% |  |  | 2022-03-31 | Ready | 0
2022-04-09 | 67 |  | Book IV Chapter IV Of The Requisites Of A Philosophical Language, And The Principles Of Definition Parts 5 through 6 | 2 of 2 | 473 | 6 | 5314 | 0:34 | 37:17 | 347882 | 73.24% |  |  | 2022-03-31 | Ready | 0
2022-04-10 | 68 | Y | Book IV Chapter V On The Natural History Of The Variations In The Meaning Of Terms |  | 480 | 7 | 5377 | 0:36 | 37:53 | 353259 | 74.37% |  |  | 2022-04-01 |  | 0
2022-04-11 | 69 |  | Book IV Chapter VI The Principles Of A Philosophical Language Further Considered |  | 487 | 7 | 7253 | 0:48 | 38:40 | 360512 | 75.9% |  |  | 2022-04-02 |  | 0
2022-04-12 | 70 |  | Book IV Chapter VII Of Classification, As Subsidiary To Induction |  | 497 | 10 | 7196 | 0:48 | 39:28 | 367708 | 77.41% |  |  | 2022-04-02 |  | 0
2022-04-13 | 71 |  | Book IV Chapter VIII Of Classification By Series |  | 507 | 10 | 2937 | 0:20 | 39:48 | 370645 | 78.03% |  |  | 2022-04-03
2022-04-13 | 72 |  | Book V. On Fallacies. Chapter I. Of Fallacies In General |  | 512 | 5 | 2321 | 0:15 | 40:03 | 372966 | 78.52% |  |  | 2022-04-03
2022-04-13 | 73 |  | Book V Chapter II Classification Of Fallacies |  | 515 | 3 | 2961 | 0:19 | 40:23 | 375927 | 79.15% |  |  | 2022-04-03
2022-04-14 | 74 | Y | Book V Chapter III Fallacies Of Simple Inspection; Or A Priori Fallacies Parts 1 through 5 | 1 of 2 | 520 | 5 | 7227 |  | 40:23 | 383154 | 80.67%
2022-04-15 | 75 |  | Book V Chapter III Fallacies Of Simple Inspection; Or A Priori Fallacies Parts 6 through 8 | 2 of 2 | 529 | 9 | 6357 |  | 40:23 | 389511 | 82%
2022-04-16 | 76 |  | Book V Chapter IV Fallacies Of Observation |  | 538 | 9 | 6161 |  | 40:23 | 395672 | 83.3%
2022-04-17 | 77 |  | Book V Chapter V Fallacies Of Generalization parts 1 through 5 | 1 of 2 | 547 | 9 | 4458 |  | 40:23 | 400130 | 84.24%
2022-04-18 | 78 | Y | Book V Chapter V Fallacies Of Generalization parts 6 through 8 | 2 of 2 | 553 | 6 | 4537 |  | 40:23 | 404667 | 85.2%
2022-04-18 | 79 |  | Book V Chapter VI Fallacies Of Ratiocination |  | 559 | 6 | 2850 |  | 40:23 | 407517 | 85.8%
2022-04-19 | 80 | Y | Book V Chapter VII Fallacies Of Confusion Part 1 | 1 of 2 | 563 | 4 | 5760 |  | 40:23 | 413277 | 87.01%
2022-04-20 | 81 | Y | Book V Chapter VII Fallacies Of Confusion Parts 2 through 3 | 2 of 2 | 571 | 8 | 5540 |  | 40:23 | 418817 | 88.17%
2022-04-20 | 82 |  | Book VI Chaoter 1 On The Logic Of The Moral Sciences |  | 579 | 8 | 1500 |  | 40:23 | 420317 | 88.49%
2022-04-21 | 83 |  | Book VI Chapter II Of Liberty And Necessity |  | 581 | 2 | 3796 |  | 40:23 | 424113 | 89.29%
2022-04-21 | 84 |  | Book VI Chapter III That There Is, Or May Be, A Science Of Human Nature |  | 586 | 5 | 2149 |  | 40:23 | 426262 | 89.74%
2022-04-22 | 85 |  | Book VI Chapter IV Of The Laws Of Mind |  | 589 | 3 | 5143 |  | 40:23 | 431405 | 90.82%
2022-04-23 | 86 | Y | Book VI Chapter V Of Ethology, Or The Science Of The Formation Of Character |  | 597 | 8 | 6749 |  | 40:23 | 438154 | 92.25%
2022-04-23 | 87 |  | Book VI Chapter VI General Considerations On The Social Science |  | 605 | 8 | 1687 |  | 40:23 | 439841 | 92.6%
2022-04-24 | 88 |  | Book VI Chapter VII Of The Chemical, Or Experimental, Method In The Social Science |  | 608 | 3 | 3813 |  | 40:23 | 443654 | 93.4%
2022-04-24 | 89 |  | Book VI Chapter VIII Of The Geometrical, Or Abstract, Method |  | 614 | 6 | 3779 |  | 40:23 | 447433 | 94.2%
2022-04-25 | 90 |  | Book VI Chapter IX Of The Physical, Or Concrete Deductive, Method |  | 619 | 5 | 7888 |  | 40:23 | 455321 | 95.86%
2022-04-26 | 91 |  | Book VI Chapter X Of The Inverse Deductive, Or Historical, Method Parts 1 through 5 | 1 of 2 | 630 | 11 | 4364 |  | 40:23 | 459685 | 96.78%
2022-04-27 | 92 |  | Book VI Chapter X Of The Inverse Deductive, Or Historical, Method Parts 6 through 8 | 2 of 2 | 637 | 7 | 5185 |  | 40:23 | 464870 | 97.87%
2022-04-28 | 93 |  | Book VI Chapter XI Additional Elucidations Of The Science Of History |  | 644 | 7 | 6391 |  | 40:23 | 471261 | 99.22%
2022-04-28 | 94 |  | Book VI Chapter XII Of The Logic Of Practice, Or Art; Including Morality And Policy |  | 652 | 8 | 3724 |  | 40:23 | 474985 | 100%
|  |  | Footnotes |  | 659
TOTAL | [5 empty] | 652 | 474985 | 40:23
TO DATE | [5 empty] | 2022-04-03 | 0
% COMPLETE
AVERAGE | [5 empty] | 6.9362 | 5053.0319 | 0:33
MAXIMUM | [5 empty] | 11 | 9148 | 1:01
RATES

## Sections
Date | Sec | Section title | Page | Words | Length | Record | WordsCum | Target | LengthCum | uploaded | PLOK
2022-02-16 | 1 | Preface To The First Edition | 3 | 1103 | 0:08 | 1:42 | 1103 | 6798 | 0:08
2022-02-17 | 2 | Preface To The Third And Fourth Editions | 2 | 714 | 0:04 | 1:48 | 1817 | 13596 | 0:12
2022-02-18 | 3 | Introduction | 12 | 5958 | 0:36 | 0:42 | 7775 | 20394 | 0:49
2022-02-19 | 4 | Book I Of Names And Propositions | 6 | 2610 | 0:16 | 0:04 | 10385 | 27192 | 1:05
2022-02-20 | 5 | Book I Chapter II Of Names | 22 | 12057 | 1:22 | 5:12 | 22442 | 33990 | 2:27
2022-02-21 | 6 | Book I Chapter III Of The Things Denoted By Names | 32 | 16225 | 1:44 | 5:42 | 38667 | 40788 | 4:11
2022-02-22 | 7 | Book I Chapter IV Of Propositions | 10 | 4783 | 0:32 | 1:48 | 43450 | 47586 | 4:43
2022-02-23 | 8 | Book I Chapter V Of The Import Of Propositions | 23 | 11591 | 1:13 | 5:06 | 55041 | 54384 | 5:56
2022-02-24 | 9 | Book I Chapter VI Of Propositions Merely Verbal | 9 | 4318 | 0:27 | 1:30 | 59359 | 61182 | 6:23 |  | 12:04 | time | 112490 | words
2022-02-25 | 10 | Book I Chapter VII Of The Nature Of Classification, And The Five Predicables | 17 | 8072 | 0:51 | 2:24 | 67431 | 67980 | 7:14 |  | 17 | days
| 11 | Book I Chapter VIII Of Definition | 22 | 12036 | 1:11 |  | 79467 | 74778 | 8:25 |  | 724 | minutes
2022-02-27 | 12 | Book II Of Reasoning | 9 | 3875 | 0:25 |  | 83342 | 81576 | 8:50 |  | 42.5882 | minutes/day | 6617.0588 | words/day
2022-02-28 | 13 | Book II Chapter II Of Ratiocination, Or Syllogism | 21 | 7928 | 1:01 | 3:12 | 91270 | 88374 | 9:51
2022-03-01 | 14 | Book II Chapter III Of The Functions And Logical Value Of The Syllogism | 27 | 14283 | 1:29 |  | 105553 | 95172 | 11:20
2022-03-02 | 15 | Book II Chapter IV Of Trains Of Reasoning, And Deductive Sciences | 14 | 6937 | 0:44 |  | 112490 | 101970 | 12:04
2022-03-03 | 16 | Book II Chapter V Of Demonstration, And Necessary Truths | 30 | 15088 |  |  | 127578 | 108768 | 12:04
2022-03-04 | 17 | Book II Chapter VI The Same Subject Continued | 9 | 4848 |  |  | 132426 | 115566 | 12:04
2022-03-05 | 18 | Book II Chapter VII Examination Of Some Opinions Opposed To The Preceding Doctrines | 20 | 10019 |  |  | 142445 | 122364 | 12:04
2022-03-06 | 19 | Book III Of Induction | 7 | 2762 |  |  | 145207 | 129162 | 12:04
2022-03-07 | 20 | Book III Chapter II Of Inductions Improperly So Called | 20 | 9541 |  |  | 154748 | 135960 | 12:04
2022-03-08 | 21 | Book III Chapter III Of The Ground Of Induction | 9 | 4451 |  |  | 159199 | 142758 | 12:04
2022-03-09 | 22 | Book III Chapter IV Of Laws Of Nature | 9 | 3779 |  |  | 162978 | 149556 | 12:04
2022-03-10 | 23 | Book III Chapter V Of The Law Of Universal Causation | 50 | 25776 |  |  | 188754 | 156354 | 12:04
2022-03-11 | 24 | Book III Chapter VI On The Composition Of Causes | 8 | 4185 |  |  | 192939 | 163152 | 12:04
2022-03-12 | 25 | Book III Chapter VII On Observation And Experiment | 9 | 4342 |  |  | 197281 | 169950 | 12:04
2022-03-13 | 26 | Book III Chapter VIII Of The Four Methods Of Experimental Inquiry | 20 | 10087 |  |  | 207368 | 176748 | 12:04
2022-03-14 | 27 | Book III Chapter IX Miscellaneous Examples Of The Four Methods | 27 | 13808 |  |  | 221176 | 183546 | 12:04
2022-03-15 | 28 | Book III Chapter X Of Plurality Of Causes, And Of The Intermixture Of Effects | 21 | 10685 |  |  | 231861 | 190344 | 12:04
2022-03-16 | 29 | Book III Chapter XI Of The Deductive Method | 9 | 4503 |  |  | 236364 | 197142 | 12:04
2022-03-17 | 30 | Book III Chapter XII Of The Explanation Of Laws Of Nature | 9 | 4610 |  |  | 240974 | 203940 | 12:04
2022-03-18 | 31 | Book III Chapter XIII Miscellaneous Examples Of The Explanation Of Laws Of Nature | 10 | 4942 |  |  | 245916 | 210738 | 12:04
2022-03-19 | 32 | Book III Chapter XIV Of The Limits To The Explanation Of Laws Of Nature; And Of Hypotheses | 24 | 11859 |  |  | 257775 | 217536 | 12:04
2022-03-20 | 33 | Book III Chapter XV Of Progressive Effects; And Of The Continued Action Of Causes | 8 | 3763 |  |  | 261538 | 224334 | 12:04
2022-03-21 | 34 | Book III Chapter XVI Of Empirical Laws | 9 | 4497 |  |  | 266035 | 231132 | 12:04
2022-03-22 | 35 | Book III Chapter XVII Of Chance And Its Elimination | 9 | 4942 |  |  | 270977 | 237930 | 12:04
2022-03-23 | 36 | Book III Chapter XVIII Of The Calculation Of Chances | 15 | 7408 |  |  | 278385 | 244728 | 12:04
2022-03-24 | 37 | Book III Chapter XIX Of The Extension Of Derivative Laws To Adjacent Cases | 6 | 3204 |  |  | 281589 | 251526 | 12:04
2022-03-25 | 38 | Book III Chapter XX Of Analogy | 8 | 3375 |  |  | 284964 | 258324 | 12:04
2022-03-26 | 39 | Book III Chapter XXI Of The Evidence Of The Law Of Universal Causation | 17 | 7972 |  |  | 292936 | 265122 | 12:04
2022-03-27 | 40 | Book III Chapter XXII Of Uniformities Of Co-Existence Not Dependent On Causation | 13 | 6610 |  |  | 299546 | 271920 | 12:04
2022-03-28 | 41 | Book III Chapter XXIII Of Approximate Generalizations, And Probable Evidence | 14 | 6747 |  |  | 306293 | 278718 | 12:04
2022-03-29 | 42 | Book III Chapter XXIV Of The Remaining Laws Of Nature | 19 | 9359 |  |  | 315652 | 285516 | 12:04
2022-03-30 | 43 | Book III Chapter XXV Of The Grounds Of Disbelief | 16 | 8102 |  |  | 323754 | 292314 | 12:04
2022-03-31 | 44 | Book IV Of Operations Subsidiary To Induction | 9 | 4137 |  |  | 327891 | 299112 | 12:04
2022-04-01 | 45 | Book IV Chapter II Of Abstraction, Or The Formation Of Conceptions | 14 | 6819 |  |  | 334710 | 305910 | 12:04
2022-04-02 | 46 | Book IV Chapter III Of Naming, As Subsidiary To Induction | 5 | 2256 |  |  | 336966 | 312708 | 12:04
2022-04-03 | 47 | Book IV Chapter IV Of The Requisites Of A Philosophical Language, And The Principles Of Definition | 19 | 9081 |  |  | 346047 | 319506 | 12:04
2022-04-04 | 48 | Book IV Chapter V On The Natural History Of The Variations In The Meaning Of Terms | 11 | 5392 |  |  | 351439 | 326304 | 12:04
2022-04-05 | 49 | Book IV Chapter VI The Principles Of A Philosophical Language Further Considered | 14 | 7264 |  |  | 358703 | 333102 | 12:04
2022-04-06 | 50 | Book IV Chapter VII Of Classification, As Subsidiary To Induction | 14 | 7206 |  |  | 365909 | 339900 | 12:04
2022-04-07 | 51 | Book IV Chapter VIII Of Classification By Series | 7 | 2944 |  |  | 368853 | 346698 | 12:04
2022-04-08 | 52 | Book V On Fallacies | 5 | 2323 |  |  | 371176 | 353496 | 12:04
2022-04-09 | 53 | Book V Chapter II Classification Of Fallacies | 6 | 2967 |  |  | 374143 | 360294 | 12:04
2022-04-10 | 54 | Book V Chapter III Fallacies Of Simple Inspection; Or A Priori Fallacies | 28 | 13567 |  |  | 387710 | 367092 | 12:04
2022-04-11 | 55 | Book V Chapter IV Fallacies Of Observation | 14 | 6167 |  |  | 393877 | 373890 | 12:04
2022-04-12 | 56 | Book V Chapter V Fallacies Of Generalization | 18 | 8972 |  |  | 402849 | 380688 | 12:04
2022-04-13 | 57 | Book V Chapter VI Fallacies Of Ratiocination | 6 | 2856 |  |  | 405705 | 387486 | 12:04
2022-04-14 | 58 | Book V Chapter VII Fallacies Of Confusion | 22 | 11277 |  |  | 416982 | 394284 | 12:04
2022-04-15 | 59 | Book VI On The Logic Of The Moral Sciences | 4 | 1507 |  |  | 418489 | 401082 | 12:04
2022-04-16 | 60 | Book VI Chapter II Of Liberty And Necessity | 8 | 3803 |  |  | 422292 | 407880 | 12:04
2022-04-17 | 61 | Book VI Chapter III That There Is, Or May Be, A Science Of Human Nature | 5 | 2187 |  |  | 424479 | 414678 | 12:04
2022-04-18 | 62 | Book VI Chapter IV Of The Laws Of Mind | 10 | 5151 |  |  | 429630 | 421476 | 12:04
2022-04-19 | 63 | Book VI Chapter V Of Ethology, Or The Science Of The Formation Of Character | 13 | 6763 |  |  | 436393 | 428274 | 12:04
2022-04-20 | 64 | Book VI Chapter VI General Considerations On The Social Science | 4 | 1696 |  |  | 438089 | 435072 | 12:04
2022-04-21 | 65 | Book VI Chapter VII Of The Chemical, Or Experimental, Method In The Social Science | 9 | 3828 |  |  | 441917 | 441870 | 12:04
2022-04-22 | 66 | Book VI Chapter VIII Of The Geometrical, Or Abstract, Method | 8 | 3790 |  |  | 445707 | 448668 | 12:04
2022-04-23 | 67 | Book VI Chapter IX Of The Physical, Or Concrete Deductive, Method | 16 | 7900 |  |  | 453607 | 455466 | 12:04
2022-04-24 | 68 | Book VI Chapter X Of The Inverse Deductive, Or Historical, Method | 21 | 9531 |  |  | 463138 | 462264 | 12:04
2022-04-25 | 69 | Book VI Chapter XI Additional Elucidations Of The Science Of History | 14 | 6401 |  |  | 469539 | 469062 | 12:04
2022-04-26 | 70 | Book VI Chapter XII Of The Logic Of Practice, Or Art; Including Morality And Policy | 9 | 4778 |  |  | 474317 | 475860 | 12:04
|  | TOTALS | 967 | 474317 | 12:04 | 29:10
|  | AVERAGES |  | 6775.9571